PAILO AI

Your AI Partner for PLC Programming

MVP & Product Plan Autonomous TIA Portal Programming Agent Technical Specification & Development Roadmap

Author: Brijin Chacko

Date: February 2026

Version: 1.0 | Status: Active Development

CONFIDENTIAL

# Table of Contents

Table of Contents	1

1. Executive Summary	1

1.1 Product Vision	1

1.2 Target Users	1

2. Current State: What Has Been Built	1

2.1 Overall Completion Dashboard	1

2.2 Completion Summary	1

3. Technical Architecture	1

3.1 System Architecture Overview	1

3.2 Technology Stack	1

3.3 Current File Structure	1

4. The Critical Gap: TIA Portal Direct Integration	1

4.1 What TIA Portal Openness API Can Do	1

4.2 What Needs to Be Built: C# TIA Bridge	1

4.3 Prerequisites for TIA Integration	1

5. TIA Portal XML Block Generation	1

5.1 XML Generation Requirements	1

5.2 Existing Open-Source Tools	1

6. Development Roadmap	1

6.1 Phase 1: MVP - TIA Portal Integration (8-12 weeks)	1

6.2 Phase 2: Intelligence & Reliability (6-8 weeks)	1

6.3 Phase 3: Full Autonomy (8-10 weeks)	1

6.4 Phase 4: Commercial Product (10-12 weeks)	1

7. Autonomous Programming Workflow	1

7.1 The 8-Step Autonomous Pipeline	1

7.2 Self-Healing Compilation Loop	1

8. Cost & Resource Estimate	1

8.1 Development Costs	1

8.2 Timeline Summary	1

9. Risks & Mitigations	1

10. Next Immediate Actions (This Week)	1

# 1. Executive Summary

PAILO AI is an AI-powered autonomous PLC programming agent designed to write, deploy, and manage complete PLC programs inside Siemens TIA Portal with minimal human supervision. The product bridges the gap between natural language instructions and production-ready PLC code, targeting Siemens S7-1200/1500, Allen-Bradley ControlLogix, and CODESYS platforms.

The vision is a tool where a PLC engineer describes what they need in plain English, and PAILO AI generates the complete program structure, function blocks, tag lists, safety interlocks, and HMI tag bindings, then compiles and deploys it directly to TIA Portal.

## 1.1 Product Vision

From: "I need a motor starter FB with overload protection, auto/manual mode, and runtime tracking"

To: A complete, compiled FB_MotorStarter block with instance DB, tag table, and HMI faceplate tags imported into TIA Portal and ready for download to the PLC.

## 1.2 Target Users

PLC programmers, automation engineers, system integrators, and controls engineers who work with Siemens TIA Portal daily and want to dramatically accelerate their programming workflow. PAILO AI does not replace the engineer; it acts as a highly skilled assistant that handles the repetitive, boilerplate-heavy coding work.

# 2. Current State: What Has Been Built

The following table provides a complete audit of every component in the current PAILO AI codebase, its completion status, and what remains to be done.

## 2.1 Overall Completion Dashboard

| Component | Status | Completion | Notes |
| --- | --- | --- | --- |
| AI Chat Engine (plc_agent.py) | DONE | 100% | Claude API + tool loop working |
| Web UI (index.html) | DONE | 100% | Dark theme, chat, sidebar, export |
| FastAPI Server (web_app.py) | DONE | 100% | All API routes functional |
| System Prompt (system_prompt.txt) | DONE | 100% | 172 lines of PLC expertise |
| Code Generation Tool | DONE | 100% | Generates SCL/ST, auto-saves |
| Troubleshooting Tool | DONE | 100% | Structured diagnosis output |
| Code Conversion Tool | DONE | 100% | Siemens/AB/CODESYS mapping |
| Code Explanation Tool | DONE | 100% | Full code analysis |
| Tag List Generator | DONE | 100% | CSV/JSON/XML export |
| File Save Tool | DONE | 100% | Auto file extension handling |
| Knowledge Base (RAG) | PARTIAL | 70% | Builder ready, needs docs populated |
| TIA Portal Bridge Server | PARTIAL | 40% | Flask API ready, needs C# EXE |
| TIA Portal C# Bridge EXE | NOT STARTED | 0% | Core missing piece |
| VPS Deployment | DONE | 100% | Live at plc.oforo.ai |
| Code Templates | PARTIAL | 30% | 2 templates, needs 15+ more |
| Authentication/Users | NOT STARTED | 0% | No login system yet |
| TIA XML Block Generator | NOT STARTED | 0% | Needed for direct TIA import |
| HMI Tag Generation | NOT STARTED | 0% | WinCC tag export not built |
| Multi-project Support | NOT STARTED | 0% | Single session only |

## 2.2 Completion Summary

| 10 of 19 Components Complete | 3 of 19 Partially Built | 6 of 19 Not Started |
| --- | --- | --- |

Estimated Overall Completion: ~55% (AI chat engine is fully functional; TIA Portal integration is the major gap)

# 3. Technical Architecture

PAILO AI uses a three-tier architecture connecting a web-based chat interface, an AI agent backend, and the TIA Portal engineering environment on a Windows PC.

## 3.1 System Architecture Overview

SYSTEM ARCHITECTURE [USER BROWSER] --- HTTPS ---> [WEB UI: index.html] ¦ [FastAPI Server] ¦ [PAILO AI Agent Engine] / ¦ \ [Claude API] [RAG KB] [Tool Router] ¦ [TIA Bridge Flask Server] (Windows PC, port 5050) ¦ [TIA Portal Openness API + C#]

## 3.2 Technology Stack

| Layer | Technology | Details |
| --- | --- | --- |
| AI Engine | Claude Sonnet 4.5 API | Anthropic API with tool use, multi-turn conversation |
| Backend | Python 3.12 + FastAPI | Async web server, tool routing, file management |
| Frontend | Single-file HTML/CSS/JS | Dark theme chat UI with Jinja2 templating |
| Knowledge Base | ChromaDB + LangChain | RAG with HuggingFace embeddings (all-MiniLM-L6-v2) |
| TIA Bridge | Flask (Python) + C# (.NET) | REST API on Windows relaying to TIA Openness API |
| TIA Integration | Siemens.Engineering.dll | TIA Portal Openness API (V18-V20, .NET 4.8) |
| Deployment | Ubuntu 22 VPS (Hostinger) | Nginx reverse proxy, systemd service, SSL |
| Domain | plc.oforo.ai | Hostinger DNS, subdomain pointing to VPS |

## 3.3 Current File Structure

| File | Lines | Purpose |
| --- | --- | --- |
| plc_agent.py | 605 | Core AI agent: tool definitions, handlers, conversation loop |
| web_app.py | 161 | FastAPI server: routes for chat, reset, bridge, file ops |
| index.html | 643 | Complete chat UI: CSS + HTML + JS in single file |
| system_prompt.txt | 172 | Expert PLC knowledge: platforms, standards, code rules |
| config.py | 76 | Environment config loader from .env |
| build_knowledge_base.py | 183 | RAG builder: loads docs, chunks, embeds into ChromaDB |
| tia_bridge_server.py | 279 | Windows bridge: Flask API for TIA Portal commands |
| setup.sh | 132 | Mac one-click installer: venv, pip, directory structure |
| requirements.txt | 32 | 17 Python dependencies |
| TOTAL | ~2,300 | Lines of production code |

# 4. The Critical Gap: TIA Portal Direct Integration

The single biggest piece missing to achieve the vision of PAILO AI autonomously writing programs inside TIA Portal is the C# Bridge Application that interfaces with the TIA Portal Openness API. Currently, the Flask bridge server is ready to relay commands, but the actual C# executable that talks to TIA Portal does not exist yet.

## 4.1 What TIA Portal Openness API Can Do

The Siemens TIA Portal Openness API (Siemens.Engineering.dll) provides programmatic access to nearly every engineering function in TIA Portal. This is the technology that makes autonomous PLC programming possible.

| Capability | API Support | PAILO AI Usage |
| --- | --- | --- |
| Create/open TIA projects | DONE | Create project from scratch for new machines |
| Import SCL/ST blocks (FB, FC, OB) | DONE | Import AI-generated code blocks via XML |
| Create Data Blocks (DB, IDB) | DONE | Generate instance DBs for function blocks |
| Define/import tag tables | DONE | Create full tag lists from system description |
| Compile PLC software | DONE | Compile after code import, report errors |
| Download to PLC hardware | DONE | Push compiled program to physical PLC |
| Export blocks as XML | DONE | Read existing code for analysis/modification |
| Create User-Defined Types | DONE | Generate UDTs for structured data |
| Hardware configuration | PARTIAL | Read/modify S7-1500 module parameters |
| HMI screen manipulation | PARTIAL | Tag binding (limited visual design) |
| Live PLC data read/write | NOT STARTED | Requires separate protocol (Snap7/OPC UA) |

## 4.2 What Needs to Be Built: C# TIA Bridge

The C# TIA Bridge is a Windows console application (.exe) that accepts command-line arguments from the Flask bridge server and executes TIA Portal Openness API calls. This is the most technically complex component of the entire product.

| Bridge Command | What It Does |
| --- | --- |
| import-block <project> <name> <scl_file> | Imports an SCL source file as a new block into the TIA project |
| compile <project> | Compiles the entire PLC software and returns success/error with details |
| export-block <project> <name> <output> | Exports a block as XML for AI analysis or backup |
| list-blocks <project> | Lists all blocks (FB, FC, OB, DB) in the project with metadata |
| create-project <path> <cpu_type> | Creates a new TIA project with specified CPU and default config |
| import-tags <project> <csv_file> | Imports a CSV tag table into the PLC tag management |
| download <project> <device_ip> | Downloads compiled program to the physical PLC via network |
| create-db <project> <name> <udt_ref> | Creates a data block (instance or global) from UDT reference |

## 4.3 Prerequisites for TIA Integration

| Requirement | Details |
| --- | --- |
| Windows 10/11 PC | TIA Portal only runs on Windows (the Mac runs the AI, the PC runs TIA) |
| TIA Portal V18 or newer | V18+ recommended for stable Openness API and long-term support |
| .NET Framework 4.8 | Required runtime for the C# bridge application |
| Visual Studio 2022 | Free Community edition is sufficient for building the C# project |
| Siemens TIA Openness group | Windows user must be added to the Siemens TIA Openness user group |
| Same network (LAN/VPN) | Mac and Windows PC must be able to communicate on the same network |
| Anthropic API key | For Claude API calls (already configured in your .env) |

# 5. TIA Portal XML Block Generation

TIA Portal Openness imports blocks as XML files, not raw SCL text. The AI currently generates SCL code, but to import it directly into TIA Portal, PAILO AI needs a TIA XML Generator module that wraps the SCL code in the correct XML structure.

## 5.1 XML Generation Requirements

Every block imported via Openness must be wrapped in a specific XML schema that includes the block type, interface definition (VAR sections), network structure, and compilation metadata. The AI must generate this XML programmatically.

| XML Element | Priority | Description |
| --- | --- | --- |
| Block envelope (FB/FC/OB/DB) | Critical | Root XML structure with block type, name, number, version |
| Interface definition | Critical | VAR_INPUT, VAR_OUTPUT, VAR_IN_OUT, VAR, VAR_TEMP sections |
| SCL network body | Critical | Actual code wrapped in network/statement containers |
| Compilation attributes | High | S7_Optimized_Access, memory layout, block properties |
| UDT definitions | High | Structured data types referenced by blocks |
| Instance DB from FB | High | Auto-generate instance data blocks for function blocks |
| Comment blocks | Medium | Block header comments, version info, author |
| Know-how protection | Low | Optional encryption for IP protection |

## 5.2 Existing Open-Source Tools

Several open-source libraries can help with XML generation, reducing development time significantly:

| Library | Language | What It Does |
| --- | --- | --- |
| tia-portal-xml-generator | Python | Generates XML files for DB, FB, OB block import (MIT license) |
| TiaUtilities | C# | Import/export XML, code generation for TIA blocks |
| CodeGeneratorOpenness | C# | Demonstrates code generation via Openness API |
| tia-openness-api-client | Python | Complete Python wrapper for Openness via pythonnet |

# 6. Development Roadmap

The roadmap is organized into four phases, each building on the previous one. Phase 1 is the MVP that delivers core TIA Portal integration. Subsequent phases add intelligence, scale, and commercial readiness.

## 6.1 Phase 1: MVP - TIA Portal Integration (8-12 weeks)

Goal: PAILO AI can generate a complete PLC program from a description and import it into TIA Portal, compile it, and report success/errors.

| # | Task | Effort | Priority | Dependencies |
| --- | --- | --- | --- | --- |
| 1 | Build C# TIA Bridge console app | 3-4 weeks | CRITICAL | Visual Studio, TIA Portal |
| 2 | Implement import-block command | 1 week | CRITICAL | Task 1 |
| 3 | Implement compile command | 3 days | CRITICAL | Task 1 |
| 4 | Implement export-block command | 3 days | HIGH | Task 1 |
| 5 | Build TIA XML generator module | 2 weeks | CRITICAL | Python, XML schema docs |
| 6 | Integrate XML gen with AI agent | 1 week | CRITICAL | Task 5 |
| 7 | Add compile error feedback loop | 1 week | HIGH | Tasks 3, 6 |
| 8 | Build tag table XML import | 3 days | HIGH | Task 5 |
| 9 | Create 15+ code templates | 1 week | MEDIUM | None |
| 10 | End-to-end testing workflow | 1 week | CRITICAL | All above |

## 6.2 Phase 2: Intelligence & Reliability (6-8 weeks)

Goal: PAILO AI can handle complex multi-block programs, fix its own compilation errors, and learn from your project patterns.

| # | Task | Effort | Priority | Dependencies |
| --- | --- | --- | --- | --- |
| 1 | Self-healing compilation loop | 2 weeks | CRITICAL | Phase 1 complete |
| 2 | Multi-block project generation | 2 weeks | HIGH | Phase 1 |
| 3 | Populate knowledge base with docs | 1 week | HIGH | PLC manuals collection |
| 4 | Instance DB auto-generation | 1 week | HIGH | XML generator |
| 5 | UDT definition generator | 3 days | MEDIUM | XML generator |
| 6 | Safety block templates (F-CPU) | 1 week | MEDIUM | Safety expertise |
| 7 | Code review / best practice checker | 1 week | MEDIUM | System prompt enhancement |
| 8 | Project backup/versioning | 3 days | LOW | None |

## 6.3 Phase 3: Full Autonomy (8-10 weeks)

Goal: PAILO AI can take a system specification and produce a complete, downloadable TIA Portal project with minimal supervision.

| # | Task | Effort | Priority | Dependencies |
| --- | --- | --- | --- | --- |
| 1 | Complete project scaffolding (OB1 + FBs + DBs) | 2 weeks | CRITICAL | Phase 2 |
| 2 | Hardware config from spec (CPU + IO selection) | 2 weeks | HIGH | Openness HW API |
| 3 | HMI tag table generation for WinCC | 1 week | HIGH | HMI Openness API |
| 4 | Download-to-PLC integration | 1 week | HIGH | Phase 1 bridge |
| 5 | OPC UA / Snap7 runtime monitoring | 2 weeks | MEDIUM | Separate comm layer |
| 6 | Allen-Bradley L5X export support | 1 week | MEDIUM | AB file format spec |
| 7 | Project comparison / diff tool | 1 week | LOW | Export functionality |

## 6.4 Phase 4: Commercial Product (10-12 weeks)

Goal: PAILO AI is a sellable SaaS product with user accounts, billing, and a polished user experience.

| # | Task | Effort | Priority | Dependencies |
| --- | --- | --- | --- | --- |
| 1 | User authentication (login/signup) | 1 week | CRITICAL | None |
| 2 | Multi-tenant project management | 2 weeks | CRITICAL | Auth system |
| 3 | Stripe billing integration | 1 week | HIGH | Auth system |
| 4 | Usage tracking & rate limiting | 3 days | HIGH | Auth system |
| 5 | Professional UI redesign (React) | 3 weeks | MEDIUM | None |
| 6 | Marketing website + docs | 2 weeks | HIGH | None |
| 7 | Enterprise SSO / team features | 2 weeks | LOW | Auth system |
| 8 | Desktop app (Electron wrapper) | 2 weeks | LOW | React UI |

# 7. Autonomous Programming Workflow

This section describes the complete end-to-end workflow for how PAILO AI will autonomously write a program inside TIA Portal, from user input to compiled code.

## 7.1 The 8-Step Autonomous Pipeline

| Step | Action | Technical Detail |
| --- | --- | --- |
| 1 | User Input | Engineer types: "Create a conveyor system with 3 motors, VFD control, safety interlocks, and a PackML state machine" |
| 2 | AI Analysis | Claude parses the request, identifies required blocks (FB_Motor x3, FB_Conveyor, FB_PackML, OB1), tags, and UDTs |
| 3 | Code Generation | AI generates complete SCL code for each block using platform-specific syntax rules from system prompt |
| 4 | XML Wrapping | Python XML generator wraps each SCL block in TIA-compatible XML with proper interface definitions |
| 5 | TIA Import | C# bridge imports each XML block into the TIA Portal project via Openness API calls |
| 6 | Tag Import | CSV tag table is generated and imported: DI_Conveyor1_Running, AI_Motor1_Speed, etc. |
| 7 | Compile | C# bridge triggers full compilation; if errors occur, AI reads error messages, fixes code, re-imports, and recompiles |
| 8 | Report | PAILO AI reports success: blocks created, compilation status, warnings, and offers to download to PLC |

## 7.2 Self-Healing Compilation Loop

The self-healing loop is what makes PAILO AI truly autonomous. When compilation fails, the agent reads the compiler errors, understands them in context, modifies the code, and retries. This loop runs up to 5 iterations before escalating to the engineer.

SELF-HEALING COMPILATION LOOP 1. Generate SCL code --> 2. Wrap in XML --> 3. Import to TIA 4. Compile --> 5. IF errors: read error log 6. AI analyzes errors --> 7. Fix code --> 8. Re-import 9. Recompile --> 10. IF success: report --> ELSE: loop (max 5x)

# 8. Cost & Resource Estimate

## 8.1 Development Costs

| Item | Cost Estimate | Notes |
| --- | --- | --- |
| Anthropic API (Claude) | $50-200/month | Depends on usage volume during dev |
| Hostinger VPS (current) | $10-15/month | Already deployed and running |
| Domain (oforo.ai) | $15-30/year | Already owned |
| TIA Portal V18+ license | $1,500-5,000 | May already have; V18 Pro needed |
| Visual Studio 2022 Community | Free | Sufficient for C# bridge development |
| Windows PC/VM for TIA | $0-1,500 | Use existing PC or Parallels on Mac |
| Total Setup Cost | $1,575-6,745 | One-time (mostly TIA Portal license) |
| Monthly Operating | $60-215/month | API + hosting + domain |

## 8.2 Timeline Summary

| Phase | Duration | Outcome |
| --- | --- | --- |
| Phase 1: MVP | 8-12 weeks | Code generates, imports into TIA, compiles |
| Phase 2: Intelligence | 6-8 weeks | Self-healing, multi-block, knowledge base |
| Phase 3: Full Autonomy | 8-10 weeks | Complete project generation, HMI, download |
| Phase 4: Commercial | 10-12 weeks | User accounts, billing, polished product |
| TOTAL | 32-42 weeks | Full commercial product |

# 9. Risks & Mitigations

| Risk | Severity | Mitigation |
| --- | --- | --- |
| TIA Openness API version breaks | PARTIAL | Target V18+ for long-term stability; abstract API calls behind version adapter |
| AI generates non-compilable code | PARTIAL | Self-healing loop (5 retries); validate XML before import; expand template library |
| Windows-only TIA Portal requirement | PARTIAL | Flask bridge decouples Mac/Linux AI from Windows TIA; works over LAN/VPN |
| Anthropic API cost at scale | PARTIAL | Cache common patterns; use smaller models for simple tasks; local model fallback |
| Complex safety-critical code errors | NOT STARTED | Never auto-download safety code; require engineer review; add verification step |
| Siemens licensing restrictions | PARTIAL | Openness is included with TIA Portal license; no additional cost for API access |
| Competitor products emerging | PARTIAL | First-mover advantage; deep PLC domain expertise as moat; community templates |

# 10. Next Immediate Actions (This Week)

These are the concrete steps you can take right now to move toward the Phase 1 MVP:

| # | Action | Time | What You Need |
| --- | --- | --- | --- |
| 1 | Set up Windows environment: Install TIA Portal V18+, Visual Studio 2022 Community, .NET 4.8 SDK | 2-3 hours | Windows PC or Parallels VM |
| 2 | Add yourself to Siemens TIA Openness Windows user group | 10 min | Admin access on Windows |
| 3 | Create a test C# console app that opens TIA Portal via Openness | 1-2 hours | VS 2022 + Siemens.Engineering.dll |
| 4 | Test: create a project, import one SCL block, compile it | 2-3 hours | Step 3 working |
| 5 | Clone the tia-portal-xml-generator repo and study the XML format | 1 hour | GitHub account |
| 6 | Populate knowledge/ directory with your actual PLC manuals and code examples | 1 hour | Your PLC project files |
| 7 | Run build_knowledge_base.py to build the RAG database | 30 min | Step 6 done |

KEY TAKEAWAY You have built 55% of PAILO AI. The AI brain is fully functional. The single biggest gap is the C# TIA Bridge executable that connects your AI to TIA Portal. Once that bridge is built, you have a working autonomous PLC programming agent. The technology exists. The API supports it. You just need to connect the two worlds.